Limited-Preemptive Malleable Elastic Gang Scheduling (LPMEGS)
Weekly Meeting
Joan Marcè i Igual
12th of February, 2020

---
What has been done?
- Finish part of paper
  - Proofs of new formulae
  - Related work
- Decide in full LPMEGS implementation
  - Reservation part
  - Assigning cores with multiple objectives

---
What has been done?
- Objectives decided
  - Take task with higher
  - Priority
- Start writing simulation
  - JLFP implemented
  - LPMEGS implemented
  - Results are missing
- Decide in more or less what has to be prepared for CAPITAL

---
Problems found in LPMEGS
- Finding it’s a difficult task. Possible solutions:
  - Change objective
  - Find a better way to compute (maybe I don’t know how to do it properly)
- When a previously scheduled task is the one limiting the value of . Default action:
  - Just jump to the next objective since there’s nothing we can do
A_{ cores reserved }^{ max }
A_{ cores reserved }^{ max }

---
What’s next?
- Review paper in progress and apply feedback
- Get some results in LPMEGS performance
  - Best way to show results?
  - Utilization-Schedulability plot?
  - Find a way to properly visualize scheduled jobs to debug algorithm implementation.
    - PlotSched looks incomplete => Send e-mail asking for possible non-released code?
    - Look for other alternatives